## Sheet1
Date | Task | Dependency | Importance | Effort | Owner | Stage | Desciption
2013-12-02 | Finish Documentation | 11, 16 | xxx | xxx |  | Not Started | Collector
2013-12-02 | Finish Program | 4,5,6, 16 | xxx | xxx |  | Not Started | Collector
2013-12-02 | Finish Front End | 7.8 | xxx | xxx |  | Not Started | Collector
2013-12-02 | Finish Back-end | 10, 12, 13, 15 | xxx | xxx |  | Not Started | Collector
2013-12-02 | Finish DB | 10 | xxx | xxx |  | Not Started | Collector
| Proto front end | 9 | xx | xxx |  | Not Started | Basic HTML and javascript implementation of the given design (AJAX included)
| Fancy front end | 7 | xxx | xxx |  | Not Started | Stylish implementation and javascript improvements
| Front end design | 0 | x | x |  | Not Started | Graphical plans and blueprints of the UI, pages, webapp structure etc. (inkscape)
| Models | 11 | xx | xx |  | Not Started | POCO classes of the defined UML structure diagrams
| UML for main models | 0 | xx | xx |  | Not Started | Static structure, class diagrams, architecture
| Web back logic implementation | 14 | xxx | xxx |  | Not Started | The controller classes implementations and the view logic
| DAL implementation | 6 | xx | x |  | Not Started | *Entities for managing object instances
| Error webpages and other misc. | 7, 12 | xx | xx |  | Not Started | Expect and handle all dirty cases of use
| Glue back end | 10,12,13 | x | xx |  | Not Started | Make things work together form tasks (10 - 12 - 13 )
| Manual testing / screen shots | 3 | x |  |  | Not Started | Go through the page a few times, try as many use cases as possibble, document it with screenshots
| Attribute Model classes for DB | 10 | x | x |  | Not Started | Make model classes work with the entity framework
| File uploading |  | xxx | xxx |  | Not Started | Implement file uploading - writing / downloading - reading filewise
| File versioning |  | xxx | xxx |  | Not Started | The task includes the things related to the versioning and writing files
| Access control |  | xxx | xxx |  | Not Started | Tokens, read/write rights, etc.
| User database |  | xxx | xxx |  | Not Started | Registering, and authenticating users
| Ajax |  | xx | xxx |  | Not Started | Client side logic for requests, BL-wise repsonses and stuff
| Style |  | x | xxx |  | Not Started | CSS for metro-like appearance
| GIT |  | x | xxx |  | Not Started | :(
| Search |  | xx | xx |  | Not Started | Searching and meta info
| Group / project management impl. |  | xxx | xx |  | Not Started | Group and project - creating / inviting / renominating, etc
| Write documentation for GUI |  | xxx | xx |  | Not Started | No comment
| Write documentation for DAO |  | xxx | xx |  | Not Started | No comment
| Write documentation for BL |  | xxx | xx |  | Not Started | No comment
2013-12-09 | PPT task | 2.3 | xxx | x |  | Not Started | Tasks documentation and ppt
| Integrate UI to View | 7 | x | x |  | Not Started | make ui razor compatible, and integrate C# code snippets
| BUG FIX |  | xxx | xxx |  | Not Started | WAT?!